## Actions for 2026-2030
Annex No 2 to Decision of the Government of the Republic of Armenia No 30-L of 8 January 2026
Action Plan of Implementation of the 2026-2030 Strategic Plan for Tourism Development of the Republic of Armenia
* The target monitoring indicators of the 2026-2030 Strategic Plan for Tourism Development of the Republic of Armenia are presented in Table 1 of this Annex
N | STRATEGIC GOALS, PRIVATE GOALS, ACTIONS | DESCRIPTION OF ACTIONS | RESPONSIBLE BODY | CO-IMPLEMENTING BODY | DEADLINE | FINANCING (AMD THOUSAND) |  |  |  |  | FINANCING TOTAL (AMD THOUSAND) | SOURCE OF FINANCING
[6 empty] | 2026 | 2027 | 2028 | 2029 | 2030
1 | SYSTEMATIC ACTIONS
1.1 | Improving statistics on tourist visits | Improve the systems of collection and analysis of data on inbound and domestic tourism, providing data by territorial distribution, demographic data of visitors, purpose and duration of visit, etc. Forming a database on persons providing tourism services, taking as a basis the data of the electronic register regarding persons providing tourism services Collect information about domestic tourist visits from persons providing tourism services having notified about activities Ensure the availability of information about regional distribution, purposes of visits, gender-age composition of domestic, inbound and outbound tourist visits and one-day visitors and other information | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Statistical Committee of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year | 5000 | 7000 | 7000 | 10000 | 10000 | 39000 | State Budget of the Republic of Armenia
1.2 | Conducting periodic cost-benefit analyses and monitoring of effectiveness of marketing activities | Conduct assessment of tourism marketing activities on a regular basis, by applying Key Performance Indicators (KPIs), i.e. accessibility, engagement, transformation indicators and Return on Investment (ROI) Carry out activities aimed at improving strategies in the tourism sector and budget distributions (redistributions), based on the conducted analyses | Tourism Committee of the Ministry of Economy of the Republic of Armenia | - | 2026-2030 Until the second ten-day period of December of each year | - | - | - | - | - | - | No financing is envisaged
1.3 | Regulating the existing problems in the tourism sector and issues beyond the functions and powers of the body developing the state policy | Including issues related to the tourism sector in the agenda for sessions of the inter-agency working group to be set up as part of the Strategy for Economic Transformation and Sustainable Development for regulating the current problems in the tourism sector | Tourism Committee of the Ministry of Economy of the Republic of Armenia | - | 2026-2030 Until the second ten-day period of December of each year | - | - | - | - | - | - | No financing is envisaged
1.4 | Adopting the draft Decision of the Prime Minister of the Republic of Armenia "On approving the Action Plan aimed at improving the competitiveness of tourism in Armenia" | Regular activities with state bodies of the Republic of Armenia for implementation of the activities envisaged by the Action Plan for Improving the competitiveness of tourism in the areas of co-ordination of the state bodies; gathering and summarisation of the reports thereon; analysis of problems and the development and implementation of proposals for solutions to those problems. Improving the position of Armenia in the Travel and Tourism Development Index: - Ongoing implementation of processes for simplification of the procedures for reciprocal tourist visits and facilitation of the requirements for entry visa; - Implementing co-operation with communities, particularly among the population; presenting the importance and significance of tourism to the public, particularly among the population; ongoing implementation of awareness-raising activities, etc. | Tourism Committee of the Ministry of Economy of the Republic of Armenia | - | 2026-2030 Until the second ten-day period of December of each year | - | - | - | - | - | - | No financing is envisaged
2 | Economic direction: Strategic Goal 1: Full use of economic potential of tourism
2.1 | Promote, through decentralisation of tourism and distribution of resources, proportional territorial development for increasing the living standard of residents, overcoming poverty and creating employment opportunities. Empower the management system, set up tourist destinations (cluster) and tourist villages, ensure the smooth functioning of tourist destination management organisations (DMO).
2.1.1 | Declaration of settlements, administrative districts or administrative and territorial units containing significant tourism resources, as well as their combination, including Areni, Dilijan, Dvin, Gyumri, Jermuk, Goris, Yeghegis, as tourist destination (cluster) | Identify the regional/community-related characteristics and resources of settlements or the combination of settlements, ensure branding of tourist destinations (clusters) Ensure mapping of tourism potential of marzes, with availability of a register of tourism resources Develop a roadmap, a climate-resistant and disaster-resistant master plan and zoning plan for every tourist destination (cluster), in accordance with the national, regional and local development plans Develop a management plan for every tourist destination (cluster), with the involvement and participation of interested parties Carry out public awareness campaigns and citizen engagement activities Ensure the activities for establishing destination management organisations and organising proper activities thereof Ensure active co-operation with the private sector Organise a competition for the selection of a destination management organisation (DMO) for one marz or local tourist destination from among the qualified destination management organisations | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Territorial Administration and Infrastructure of the Republic of Armenia Ministry of Environment of the Republic of Armenia Ministry of Education, Science, Culture and Sport of the Republic of Armenia Staffs of marzpets of the Republic of Armenia Local self-government bodies (upon consent) | 2026-2030 Until the second ten-day period of December of each year | 200000 | 300000 | 300000 | 300000 | 300000 | 1400000 | State Budget of the Republic of Armenia, credit funds
2.1.2 | Declaring tourist villages, guided by the criteria aimed at promoting the local culture, nature and intangible heritage | Develop a management plan for each tourist village, with the involvement and participation of interested parties Develop support mechanisms for tourist villages Develop promotional materials for every village, guided by the local characteristics and offers |  |  | 2026-2030 Until the second ten-day period of December of each year
2.1.3 | Improving tourism infrastructures | Improve roads for the purpose of filling in the gaps of access to tourist attraction sites Place signs, marks, information panels on roads Carry out activities aimed at creating facilities designed for the provision of services to tourists Build or restore museums, tourist attraction sited fostering local economic development Develop a schedule for the implementation of activities aimed at improving infrastructures, co-ordinating it with local self-government bodies Establish relevant management systems in order to ensure sustainable and long-term operation of infrastructures | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Territorial Administration and Infrastructure of the Republic of Armenia Ministry of Education, Science, Culture and Sport of the Republic of Armenia Staffs of marzpets of the Republic of Armenia Local self-government bodies (upon consent) | 2026-2030 Until the second ten-day period of December of each year
2.2 | Ensure the strengthening of co-operation between tourism and other sectors (agriculture, healthcare, technologies, etc.) for the purpose of ensuring the development of other sectors and promote local products and services through tourism.
2001-02-02 | Ensuring cross-sectoral integration | Ensure development of specialised tour packages, by incorporating the features of local agriculture, medical, wellness and innovative technologies Facilitate the establishment of co-operation between persons providing tourism services and local manufacturers — ensure the creation of business co-operation platforms in order to establish the connection between persons providing tourism services and local suppliers Introduce a system of certificates for use of local products for persons providing hotel and catering services Ensure active inter-agency co-operation, including in the tourism, environmental, cultural and infrastructure development sectors Introduce an economic assessment toolkit for measuring and analysing — in a co-ordinated manner — the added value emerging from the tourism sector and the regional impact. | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Economy of the Republic of Armenia Ministry of Territorial Administration and Infrastructure of the Republic of Armenia Ministry of Education, Science, Culture and Sport of the Republic of Armenia Staffs of marzpets of the Republic of Armenia Local self-government bodies (upon consent) | 2027-2030 Until the second ten-day period of December of each year | - | - | - | - | - | - | No financing is required
2.2.2. | Developing routes under the title "Tourism Crossroads" along the borderline with neighbouring countries, based on the principles of sustainable, responsible tourism, connecting cultural, natural monuments, persons providing services and manufacturers, symbolising the establishment and strengthening of peace through nature and common heritage | Carry out joint nature protection campaigns and voluntary Saturday works Ensure the availability of platforms for presenting mapping and tourism resources and sharing stories on-line Present joint offers, develop regional tour packages Develop joint marketing materials and signs in at least three languages Ensure the conduct of symbolic events in borderline settlements Ensure the conduct of experience exchange events for persons providing services and manufacturers of the borderline settlements of the Republic of Armenia and neighbouring countries Ensure the availability of courses devoted to peace and stability for communities Ensure the organising of workshops targeted at capacity-building for tourism management in communities Organise familiarization visits for bloggers, celebrities and journalists Ensure a pilot opening event of the "Crossroads of Tourism", with the participation of the ministers and media representatives of the Republic of Armenia and neighbouring countries | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Economy of the Republic of Armenia Ministry of Foreign Affairs of the Republic of Armenia Ministry of Territorial Administration and Infrastructure of the Republic of Armenia Ministry of Education, Science, Culture and Sport of the Republic of Armenia Staffs of marzpets of the Republic of Armenia Local self-government bodies (upon consent) | 2027-2030 Until the second ten-day period of December of each year | - | - | - | - | - | - | No financing is required
Promote the formation of a supportive business and entrepreneurial environment in the tourism sector, by ensuring the best possible conditions for starting a business, carrying out activities and development.
2.3.1. | Introduce target systems of promotion and support for persons launching activities in the tourism sector and small and medium-sized enterprise entities | Develop support programmes for persons carrying out activities in the tourism sector Ensure availability of consulting services for economic entities at tourist destinations (clusters) Ensure availability of mentorship programmes connecting experienced and novice businessmen of the sector with each other | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Economy of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year | [6 empty] | No financing is required
2026-04-02 | Engage investments, including foreign investments, to create or develop businesses through the engagement of necessary financial resources in the tourism sector.
2.4.1 | Ensuring co-operation with internationally recognised trademarks | Present the tourism opportunities and favourable investment climate of Armenia to persons providing hotel services which are considered as international brands Ensure presentation of attractiveness of investments in the tourism sector for foreign investors Ensure the conduct of international events to which famous international brands can be invited as partners or sponsors Develop an international PR campaign under the slogan "Armenia: The Tourism Crossroads of the Caucasus" Ensure the entry of international trademarks into Armenia State support to those importing famous international trademarks, including via gratuitous provision of state property | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Economy of the Republic of Armenia Ministry of Education, Science, Culture and Sport of the Republic of Armenia Investment Support Centre | 2026-2030 Until the second ten-day period of December of each year | - | - | - | - | - | - | No financing is envisaged
2.4.2 | Ensuring investor awareness and their access to information | Ensure the availability of a comprehensive platform for investments in tourism Organise regional investment forums for the purpose of discovering the tourism potential and strengthening the public-private partnership | Ministry of Economy of the Republic of Armenia | Tourism Committee of the Ministry of Economy of the Republic of Armenia Ministry of High-Tech Industry of the Republic of Armenia Investment Support Centre | 2028-2030 Until the second ten-day period of December of each year | 0 | 0 | 30000 | 10000 | 10000 | 50000 | State Budget of the Republic of Armenia
2.5 | Ensure the sustainability of tourism entities offering organised tour packages and their growth in the target markets.
2.5.1 | Developing a relevant policy and ensuring access to markets for organised tourism development | Represent the interests of the private sector, particularly entities of tourism activities during inter-agency discussions Simplify the visa policy for new and attractive markets Develop assistance programmes for persons providing tourism services to enable them to withstand seasonal changes Organise or provide funding for Armenia to be represented under one common pavilion at major tourism exhibitions (at least 5 exhibitions per year, including specialised religious, adventure, wine, archaeological and gastronomical exhibitions) Organise familiarisation visits or assist in the organising of familiarisation visits for foreign journalists, travel bloggers, influencers or other persons associated with the tourism sector Ensure reciprocal familiarisation visits or assist in the organising of reciprocal familiarisation visits in target markets (B2B road shows) | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Foreign Affairs of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year | 200000 | 300000 | 400000 | 500000 | 600000 | 2000000 | State Budget of the Republic of Armenia, credit funds
2.5.2 | Improving tourism product and promoting business relations | Develop and publish tour itineraries, as well as national guides for designing and branding tour packages Organise B2B workshops and networking events to connect persons providing tourism services (entities of tourism activities, person providing hotel services, tour guides, etc.) Develop a B2B platform, engaging the private sector Introduce systems for qualification of tourism services in line with international standards Create quality monitoring and improvement systems |  |  | 2026-2030 Until the second ten-day period of December of each year
2.5.3 | Capacity-building, including in the digital transformation sector | Ensure activities for employees of entities of tourism sector aimed at providing training courses on the application of digital tools Support initiatives aimed at creating e-learning platforms for continuing professional development Ensure representation at international platforms with the help of digital marketing |  | Ministry of High-Tech Industry of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year
3 | International attraction direction: Strategic Goal 2. Improving the image of Armenia as an attractive tourism destination in the global market
3.1 | Position Armenia as a boutique tourist destination, by enhancing the "Armenia: The Hidden Track" tourism brand, which places emphasis on the unique combination of cultural heritage, nature and uniqueness, and promote it through comprehensive international marketing campaigns targeted at target markets and markets with potential.
3.1.1 | Adopting and implementing the Order of the Minister of Economy of the Republic of Armenia "On approving the national tourism marketing programme under the brand "Armenia: The Hidden Track"" | Develop the content for the marketing programme in the tourism sector, guided by the priority of positioning Armenia as a boutique tourist destination Develop criteria for presenting the brand and a monitoring system Create souvenirs reflecting the Armenian identity, presenting them under the brand Carry out processes for targeted presentation of the Armenian tourism product through social media, websites and branded content | Tourism Committee of the Ministry of Economy of the Republic of Armenia |  | 2026-2030 Until the second ten-day period of December of each year | 1485000 | 1913000 | 2383000 | 2900000 | 3400000 | 12081000 | State Budget of the Republic of Armenia
3.1.2 | Developing high-class content presenting Armenian heritage — laying the foundation for activities for designing a new brand | Create and promote high-quality media content presenting the history, culture, nature and heritage of Armenia, including: - ensure the creation of high-quality videos and digital content presenting the Armenian tourism product; - ensure the creation of media content presenting the history, culture of Armenia and the Armenian people, including films, soap operas and content shaped by influencers Develop a programme for disseminating content on all global platforms in order to ensure high viewership Ensure co-operation with influencers creating content Ensure the availability of support services for media production Promote active Armenian trademarks in the international market |  | Ministry of Education, Science, Culture and Sport of the Republic of Armenia Ministry of Foreign Affairs of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year
3.1.3 | Support to the conduct of cultural events, guided by representation of Armenia as a boutique tourist destination | Discover internationally attractive events and assist in their development Create or support the conduct of events presenting the new Armenian tourism product and uniqueness Develop, for international platforms, a plan for promotion of events Strengthen co-operation with cultural institutions and representatives of the culture sector Foster, through digital marketing, the development of cultural tourism itineraries — to map and classify events targeted at cultural diversity and cross-cultural dialogue (concerts, festivals, international and other republican events), promote the popularisation of Armenian culture. |  |  | 2026-2030 Until the second ten-day period of December of each year
3.1.4 | Indirect presentation of Armenia on foreign media platforms, in immersive experiences and on entertaining programmes | Engage international film production companies and those of CIS countries to produce films in Armenia Reach agreements with famous TV shows or show producers of target markets for the production of TV products created by them, including episodes of soap operas in Armenia Promote the advancement of Armenia through internationally recognised sport advertisements or the advertisements of other brands (GoPro, Fisher, Dronne, North Face, Uniqlo, etc.) Enhance co-branding and sponsorship strategies with international brands |  | Ministry of Education, Science, Culture and Sport of the Republic of Armenia Ministry of Foreign Affairs of the Republic of Armenia Ministry of Finance of the Republic of Armenia | 2027-2030 Until the second ten-day period of December of each year
3.2 | Strengthen and activate the visibility and attractiveness of Armenia in the existing and developing international markets by applying Market Penetration and Market Development strategies. Diversify markets by reducing dependence from Russian market.
3.2.1 | Strategic development and diversification of target markets, reducing dependency from one market. | Stabilise the markets in Iran, Russia and Georgia, develop the markets in Western Europe, the Gulf countries Targeted engagement: create personal content and an offer for each market Organise familiarisation visits for influencers, journalists and bloggers, by including tours: - for journalists from television companies and print media; - for influencers with over 5 million followers on social media (especially on Instagram); - for internationally popular celebrities. | Tourism Committee of the Ministry of Economy of the Republic of Armenia |  | 2026-2030 Until the second ten-day period of December of each year
3.2.2 | Managing digital marketing effectively and engaging the audience | Carry out activities for the implementation of search engine optimisation (SEO) and search engine marketing (SEM) strategies for target markets Design digital marketing campaigns, with specific and measurable results Create a performance analytics framework Direct marketing — create a database of the e-mail addresses of target groups, arrange the dissemination of monthly bulletins, including seasonal offers, events and tourist news |  |  | 2026-2030 Until the second ten-day period of December of each year
3.2.3 | Carrying out creative campaigns in target markets | Ensure the presentation of the Armenian tourism product or experiences in the pop-up format in busy urban areas of target markets Ensure interactive digital exhibitions showcasing the sights in Armenia on prominent buildings in major cities of target markets Organise "flash-mob" style cultural performances at unexpected places, mixed with Armenian music and dances Design games devoted to "Hidden Armenia" and present them in big cities, envisaging prizes for participants, i.e. an opportunity to travel to Armenia, traditional souvenirs, etc. |  |  | 2026-2030 Until the second ten-day period of December of each year
3.2.4 | Representation of Armenia in the global media industry | Representation on Premium media platforms. Position Armenia on international tourism and mass media platforms (Travel and Leisure, Conde Nast, INSIDER, INSIDER Travel, PLAYGROUND, ATTN, UNILAD Adventure, etc.) Collaborate with the leading tourism platforms, travel bloggers and media partners (NatGeo, Lonely Planet, etc.) Integrating tourism platforms. Promoting Armenia and the Armenian tourism product on international tourism platforms (Aviasales, Momondo, Skyscanner, Booking.com, Airbnb, Lonely Planet, Kayak.com, Expedia, Viator, etc.) Engage specialised journalists of famous television companies, print and on-line media, tourism shows and television companies |  |  | 2026-2030 Until the second ten-day period of December of each year
3.2.5 | Creating and disseminating marketing materials | Develop digital and print marketing materials, matched with the requirements of each market Create and stabilise dissemination networks of marketing materials in target markets Develop a mechanism for regular updates of content in order to ensure modernity of marketing materials Create multilingual marketing materials for various cultural and linguistic groups Optimise materials, according to the purpose of dissemination |  |  | 2026-2030 Until the second ten-day period of December of each year
3.2.6 | Developing direct connections, ensuring accessibility | Collaborate with international airline companies, ensuring the availability of direct flights from target markets Foster the increase in the number of flights from new markets to Armenia Design joint marketing campaigns with airline companies and tour operators Negotiate with airline companies to ensure charter flights during passive tourist season and to introduce mechanisms for appropriate subsidisation |  | Ministry of Territorial Administration and Infrastructure of the Republic of Armenia Civil Aviation Committee of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year
3.2.7 | Co-operation with markets with great potential | Conduct research to discover markets with great potential Develop target strategic approaches for markets with great potential |  |  | 2026-2030 Until the second ten-day period of December of each year
3.3 | Promote domestic tourism by using the opportunities shaped after the coronavirus pandemic.
3.3.1 | Ensuring the conduct of domestic tourism exhibitions and events | Carry out the campaign titled "Discover Your Homeland!" for journalists, bloggers, well-known celebrities having large audience in Armenia Place seasonal advertisements through panels in Yerevan and other cities of marzes Placing advertisements presenting Armenia and the Armenian tourism product on Armenian on-line platforms Placing advertisements on WiFi networks in Armenia and placing digital panels in public spaces Carrying out advertising campaigns via on-line apps (Yandex, GG, etc.) | Tourism Committee of the Ministry of Economy of the Republic of Armenia |  | 2026-2030 Until the second ten-day period of December of each year
3.3.2 | Increasing attractiveness of leisure services through measures for service and targeted promotion of leisure in the social package | Enhance services for ensuring leisure in the social package designed for domestic tourists Develop relevant strategic approaches for the passive tourist season Establish a system of methodology and assessment for measuring the growth of domestic tourism |  |  | 2026-2030 Until the second ten-day period of December of each year
3.4 | Engage the Armenian Diaspora as ambassadors and protectors of tourism.
3.4.1 | Carrying out promotional measures targeted at Diaspora of Armenians | Placing advertisements presenting Armenia and the Armenian tourism product on on-line platforms Use the opportunities of national television companies and leisure-informational video clips as a promotional tool Carrying out campaigns on platforms that are accessible for the Diaspora | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Foreign Affairs of the Republic of Armenia; | 2026-2030 Until the second ten-day period of December of each year
3.5 | Promote international co-operation, regional tourism collaborations.
3.5.1 | Strengthening foreign relations in the tourism sector and ensuring co-operation with international and regional organisations | Develop and present proposals for international agreements in the tourism sector, within the scope of co-operation Regular activities with the government agencies of foreign countries responsible for foreign relations in order for them to present Armenia as a secure and safe country for tourism Organising working sessions, forums and conferences in Armenia with tourism representatives within the scope of bilateral collaborations Submitting proposals for accession to international tourism organisations Organising relevant procedures for accession to new international organisations Organising international events in Armenia or ensuring participation of Armenia in the specified events, in co-operation with international and regional organisations Mapping international donor organisations, activating co-operation with donor organisations | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Foreign Affairs of the Republic of Armenia Office of the High Commissioner for Diaspora Affairs of the Office of the Prime Minister of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year
4. | Quality assurance direction: Strategic Goal 3․ improve tourism services
4.1 | Diversify and develop unique, experimental tourism product for the whole year (preparing tour packages based on the existing product), presenting the existing potential of cultural, gastronomical and adventure tourism destinations of Armenia, fostering the reduction of seasonality and the promotion of regular visits during the year.
4.1.1 | Designing new thematic tour itineraries, connecting tourist destinations or tourism villages declared by the Government of the Republic of Armenia | Develop tour itineraries, which will connect tourism villages and tourist destinations to each other Develop informational marks and materials Designing a system for management and maintenance of thematic tour itineraries | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Staffs of marzpets of the Republic of Armenia Local self-government bodies (upon consent) | 2026-2030 Until the second ten-day period of December of each year
4.1.2 | Developing a tourism product for the non-active season, based on the existing infrastructures | Promote wellness and rehabilitative tourism at winter sites Develop year-round religious and pilgrimage itineraries Develop drafts of the Order of the Minister of Economy of the Republic of Armenia on approving programmes for promotion of eco- and rural tourism experiences, with respect to seasonal processes, i.e. grape harvest, ensuring the introduction of an ecological certificate, etc. Ensure the availability of gastro offers during the passive season, i.e. by assisting in the organising of different festivals Develop support mechanisms for cultural institutions, persons operating sites containing tourism resources in winter months and persons providing tourism services in the marzes in winter months Apply thematic campaigns in target markets, i.e. "Winter in Armenia" campaign Co-operate with influencers, media representatives, presenting unique experiences in the winter and spring Ensure the development and promotion of seasonal tour packages, in co-operation with tour operators Develop mechanisms for extension of the season | Tourism Committee of the Ministry of Economy of the Republic of Armenia |  | 2026-2030 Until the second ten-day period of December of each year
4.1.3 | Adopting and implementing the joint Order of the Minister of Economy of the Republic of Armenia and the Minister of Health of the Republic of Armenia "On approving the Programme for Development of Medical Tourism" Adopting and implementing the Order of the Minister of Economy of the Republic of Armenia "On approving the MICE Tourism Development Programme" | Analyse the gaps in infrastructures and assess the competitiveness of directions Develop programmes for the promotion of investments Co-operate with international MICE and medical operators Identify services with great potential Introduce systems of quality standards and certification Ensure measures aimed at strengthening the guarantees of life and health for tourists, including by envisaging opportunities for co-operation between medical centres in Armenia and the insurance companies of target countries | Ministry of Health of the Republic of Armenia Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Economy of the Republic of Armenia Investment Support Center | 2026-2030 Until the second ten-day period of December of each year
4.2 | Improve the quality of tourism services, infrastructures and digital opportunities through the introduction of artificial intelligence.
4.2.1 | Introducing an electronic register of persons providing tourism services, regulating and improving the activities of persons providing tourism services | Setting requirements and criteria for persons providing tourism services, including for ensuring safe tourism services Develo+C59ping and approving procedures, requirements for the qualification of persons providing tourism services Introducing a system of qualification of tourism experiences Activating co-operation with associations of persons providing tourism services, including by providing the opportunity to participate in or carry out the qualification process in the tourism sector, and to implement measures for human resource development Reform the quality of tourist passenger transportation, rental services for vehicles, by envisaging relevant legislative amendments for regulating the activities of the persons providing the specified service Carry out legislative reforms, as a result of which the activities of persons providing services to tourists and using apartments and houses daily, will also be regulated | Tourism Committee of the Ministry of Economy of the Republic of Armenia |  | 2026-2030 Until the second ten-day period of December of each year | - | - | - | - | - | - | No financing is envisaged
4.2.2 | Creating audio-guides (in at least 3 languages) presenting Armenia and the Armenian tourism product at historical-cultural, natural sites and other tourist attractions in the Republic of Armenia | Developing relevant methodical guides, informational materials about tourist attractions in at least three languages; Developing potential options for providing audio-guides at historical-cultural, natural sites and other tourist attractions through the creation of relevant QR codes or apps, in co-operation with interested state bodies. | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Education, Science, Culture and Sport of the Republic of Armenia Ministry of Environment of the Republic of Armenia | 2027-2030 Until the second ten-day period of December of each year | 10000 | 50000 | 50000 | 50000 | 50000 | 210000 | State Budget of the Republic of Armenia
4.2.3 | Modernisation of urban and rural infrastructures, taking into consideration the importance of inclusiveness and access to infrastructures | Organise a competition for selecting one regional or local tourist destination management organisation (DMO) from among the qualified organisations managing tourist destinations Preservation, protection and restoration of tourist natural and cultural resources available in every tourism cluster Building or restoring museums, tourist attractions Improving minimum services, providing sanitary facilities, designing, upon necessity, hubs for ensuring the safety of adventure tourists, educational programmes and grant assistance programmes for small and medium-sized enterprises and for gender equality in order to meet the primary needs of tourists Provide measures for the development of transport infrastructures and itineraries Ensure the implementation of measures aimed at introducing navigation and information systems Improvement of the water supply system; upgrading and the lighting of streets; line-marking on paths for cyclists; improvement of the major parts and green areas of cities and villages, upon necessity; establishment of neighbourhoods with similar roofs; installation and maintenance of garbage bins; installation and organising of maintenance of sanitary facilities by communities (in clusters and areas adjacent to touristic sites located outside of those clusters Increasing access of a tourism cluster to foreign markets; presenting new ways of opportunities for movement; ensuring connection between tourist destinations; activating co-operation between economic entities; implementing marketing programmes fostering the growth of tourist attractions Actions of branding, marketing and promotion in the value chain of tourism Setting aside areas envisaged for festivals or similar events in selected administrative and territorial units or settlements where, upon necessity, will not be time-related restrictions for high sound or noise as a result of relevant legislative amendments Installing guiding signs, information panels in accordance with the international tourism standards on roads leading to tourist attractions, including: | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Territorial Administration and Infrastructure of the Republic of Armenia Ministry of Environment of the Republic of Armenia Ministry of Education, Science, Culture and Sport of the Republic of Armenia Ministry of High-Tech Industry of the Republic of Armenia Staffs of marzpets of the Republic of Armenia Local self-government bodies (upon consent) | 2026-2030 Until the second ten-day period of December of each yearr | 2800000 | 8100000 | 21500000 | 6700000 | 7000000 | 46100000 | State Budget of the Republic of Armenia, credit funds
4.2.3.1 | Areni | Restoring road and street networks for improving urban mobility, access to the main sights and tourist attractions Creating a network of hiking trails and establishing new camp sites in order to facilitate the activities of nature-based tourism Establishing or restoring museums and cultural centres Shaping tourism results based on the theme of wine
4.2.3.2 | Dilijan | Improving intra-urban communication and restoring road infrastructure Reducing pollution of Aghstev River and mitigating the risk of flooding, fortification or lifting of retaining walls, nature-based solutions for the restoration of riverside parts, by replanting local vegetation and improving drainage systems and the construction of pedestrian bridges for improving access to the park adjacent to Dilijan City Building a ropeway, by connecting the centre of Dilijan City to Takhta neighbourhood in order to reduce traffic jams, and also improving communication and accessibility in the city Decorating streets and creating pedestrian zones and tour itineraries Expanding public spaces and green areas Establishing or restoring museums and cultural centres
4.2.3.3 | Goris | Renovating the heritage centre, restoring homes and façades, reconstructing historical-cultural sites and protecting the cultural environment Grouping of nearby settlements under a unified brand, with thematic attractions and hiking trails, which connect the historical and natural sights of the marz to each other Shaping tourism results in the areas of cave dwellings Establishing a hiking network Cleaning the riverbed of Vararakn River
4.2.3.4 | Gyumri | Restoration of the market in Gyumri — change of designated purpose of the area, preservation of cultural heritage of the market, creation of new experience and destination for tourists Establishing a craftsmen's school for preserving and revitalising traditional Armenian crafts, paying special attention to the arts and crafts that are characteristic of Gyumri, while promoting innovation and self-sufficient business models Reconstructing and restoring streets adjacent to historical-cultural monuments Fortifying Dashtadem fortress, constructing a museum, experience pavilions
4.2.3.5 | Jermuk | Restoring a drinking hall and adjacent infrastructures Restoring the road and trails leading to the waterfall in Jermuk, constructing a bridge and sidewalks and improving the overall comfort of tourists Capital renovation of the road approaching the ropeway, creating and/or improving the look of adjacent tourism infrastructures, works for improvement of the city park Positioning Jermuk as an international wellness destination, campaigns to present and promote Jermuk in the international market
4.2.3.6 | Yeghegis | Improvement, restoration and maintenance of the infrastructure of roads, pedestrian and tourist value chains Supporting initiatives aimed at promoting cultural events, festivals and exhibitions highlighting the rich heritage and traditions of Armenia Establishing hiking trails Restoring historical-cultural sites and improving adjacent areas Capital renovation of public infrastructure networks at Yeghegis Gorge Shaping tourism experiences and infrastructures in accordance with the potential of villages
4.2.3.7 | Dvin | Improving tourism infrastructures (entrance infrastructures, internal and priority roads, lighting on streets, furnishing with panels) at the archaeological site of Dvin Constructing the museum building and a destination for archaeologists
4.2.4 | Infrastructures designed for individual passengers | Develop guiding signs and travel maps, with QR codes and audio-guides Improve access to Wifi and mobile Internet at tourist attractions Assist in the operation of hubs adapted for tourists, i.e. tourist information centres, bicycles for rent and other activities Improve the public transportation network, ensuring the suitable and effective movement of travellers and the translation of public transport routes at least in English Improving, decorating the road leading to "Zvartnots" Airport Collaborate with organisations maintaining on-line booking systems, ensuring access to, confidence in and security of services Collaborate with internationally recognised platforms (Airbnb Experiences, GetYourGuide, Culture Trip), which can help to promote the activities of persons providing individual tourism services Carry out SEO campaigns in target countries, in the relevant languages Boost the development of trendy guest houses, eco-lodges and boutique hotels Support hosts in properly admitting individual tourists -digital communication, individualisation, opinions management Ensure co-operation with bloggers, digital and remote workers and celebrities on social platforms from the United Arab Emirates, France, Germany, the United States of America, Great Britain and Germany
4.3 | Promote the principles of responsible tourism and sustainable tourism, focusing on the informed use of nature protection and cultural values, not causing harm to the latter by ensuring social development and benefits for communities and visitors.
4.1.3 | Providing support to those carrying out activities in the tourism sector for the purpose of matching sustainability certificates AND quality criteria | Carry out campaigns, organise training courses and allocate grants, promoting green and sustainable business models Raise the level of awareness by carrying out campaigns for maintaining cleanliness, sorting trash, reducing plastic, as well as introducing eco-labels at tourist destinations. | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Education, Science, Culture and Sport of the Republic of Armenia Ministry of Labour and Social Affairs of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year | 30000 | 30000 | 30000 | 30000 | 30000 | 150000 | State Budget of the Republic of Armenia
4.3.2 | Providing assistance to accessible tourism initiatives, by promoting inclusiveness | Develop accessible and inclusive tourism standards for infrastructures and services
4.4 | Establish regular trading opportunities at cultural and historical monuments of Armenia or their adjacent areas, enhancing profitable and sustainable economic activities in the cultural heritage sites of Armenia in order to increase the number of visitors, ensure funding for preservation and deepen public awareness about the value of those sites.
4.1.4 | Ensuring the development of profitable concession programmes | Develop and introduce concession programmes or strategic approaches, which will provide destination management organisations (DMO) with the opportunity to have concession management functions, taking as a basis specific criteria for preservation of cultural heritage and visitors' management Establish the scope of operation entitled to concession rights, guided by the requirements for preservation of a site that contains tourism resource Shape a profit redistribution model, according to which, a part of concession fees will be geared towards the programmes for preservation of a site containing tourism resource and development of local communities Launch transparent competition processes for engaging the commercial organisations that are interested in providing tourism services (cafes, gift shops, etc.) next to sites containing tourism resource Ensure the creation of new experiences generating income, including interactive night tours, reproduction of historical scenes or presentations of local oral culture Ensure the development of tour packages that combine the visit to a site containing tourism resource with local food, wine, crafts or cultural events, promoting long-term stay and increase of expendituires of tourists. Provide an opportunity to sell local products in the area or in specially designated zones right next to the area. | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Territorial Administration and Infrastructure of the Republic of Armenia Ministry of Environment of the Republic of Armenia Staffs of marzpets of the Republic of Armenia Local self-government bodies (upon consent) | 2026-2030 Until the second ten-day period of December of each year | 90000 | 100000 | 100000 | 130000 | 130000 | 550000 | State Budget of the Republic of Armenia, credit funds
4.4.2 | Improving local governance capacities and expanding co-operation | Ensure training for employees of destination management organisations (DMO) devoted to concession management, visitor flow management and sustainable tourism Develop digital monitoring tools in order to assess the number of visits, visitors' satisfaction and the impact on areas Develop investment guides for ensuring sustainable infrastructures Provide technical assistance to local entrepreneurs for presenting and launching business initiatives at sites containing tourism resource Promote public-private partnership
4.5 | Position Armenia as a country that offers high-quality tourism services by helping Armenia become recognised as a country that offers high-quality tourism services and promote the institutional development of the tourism sector by ensuring co-ordinated and long-term growth.
4.5.1 | Introducing a qualification system meeting international standards in the tourism sector | Develop qualification procedures, requirements for persons providing tourism services Introduce a system for qualification of tourism experiences Activate co-operation with associations of persons providing tourism services, including by providing an opportunity to participate in or implement the qualification process in the tourism sector, to carry out measures targeted at human resources development Establish monitoring and oversight mechanisms Introduce sustainable, responsible and "green" criteria, ensuring shaping of proposals for inclusive tourism for persons with limited capabilities | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Inspection Bodies' Coordination Bureau of the Office of the Prime Minister of the Republic of Armenia Ministry of Education, Science, Culture and Sport of the Republic of Armenia Ministry of Territorial Administration and Infrastructure of the Republic of Armenia Ministry of Environment of the Republic of Armenia Ministry of Foreign Affairs of the Republic of Armenia Ministry of Finance of the Republic of Armenia Ministry of Health of the Republic of Armenia Ministry of Internal Affairs of the Republic of Armenia Ministry of High-Tech Industry of the Republic of Armenia Statistical Committee of the Republic of Armenia Urban Development Committee of the Republic of Armenia Local self-government bodies (upon consent) | 2026-2030 Until the second ten-day period of December of each year | - | - | - | - | - | - | No financing is required
4.5.2 | Ensuring effectiveness of management and oversight through co-operation with interested bodies, such as ministries, inspection bodies, staffs of marzpets and local self-government bodies | Ensure regular activities with state bodies of the Republic of Armenia, according to their powers, aimed at implementation of the actions envisaged by this Action Plan and the functions of the specified state bodies, including event planning, gathering and summarisation of reports, analysis of problems, development and implementation of proposals for the solutions to those problems Reviewing the legal grounds for oversight in the tourism sector
5 | Social direction: Strategic Goal 4: Shape a sustainable tourism sector
5.1 | Develop human capital through international co-operation for target vocational education and the introduction of qualification systems that meet international standards. Foster the development of professional skills by ensuring preparedness of workers in the sector, engagement of international practice and introduction of high standards of qualification.
5.1.1 | Empowering the workforce of the Tourism Committee — the body developing and implementing the state policy in the tourism sector | Ensure proper development and implementation of the State Policy on Tourism. Increasing the number of staff positions in the Tourism Committee, taking into consideration the multi-layeredness and volume of functions, with respect to the introduction of an electronic register for persons providing tourism services, the introduction of a new qualification system (the performance of functions for voluntary qualification of tour guides, escorts, tour buses, mandatory and tour information centres of destination management organisations, tourism experiences, hotel facilities), proper conduct of assessment of the activities of persons providing tourism services, activation of international co-operation, implementation of marketing measures, functions geared towards the engagement of investments, effective co-operation of destination management organisations and other functions Ensure ongoing training and improvement of employees of the Tourism Committee | Tourism Committee of the Ministry of Economy of the Republic of Armenia | - | 2026-2030 Until the second ten-day period of December of each year | 203000 | 237000 | 242000 | 247000 | 252000 | 1181000 | State Budget of the Republic of Armenia
5.1.2 | Ensure the operation of qualified destination management organisations (DMO) at marz or local level | Develop and introduce effective systems for qualification and selection of destination management organisations, by setting clear functions, financing mechanisms and authorities Develop professional qualification standards and training courses for employees of destination management organisations, in line with the accepted international practice Introduce a system of monitoring and analysis for assessment of effectiveness and ensuring of accountability of destination management organisations Ensure the conduct of training courses for representatives of communities, employees of entities of small and medium-sized enterprises Ensure the advancement of unique tourism product and services through grants or subsidisation Expand the capacities of destination management organisations by promoting the development of sustainable tourism in regions Ensure inter-agency co-operation, particularly in the sectors of tourism, environment, culture and infrastructures Introducing a mechanism for ensuring financial stability of destination management organisations | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Territorial Administration and Infrastructure of the Republic of Armenia |  | 75000 | 76000 | 76000 | 76000 | 76000 | 379000 | State Budget of the Republic of Armenia, credit funds
5.1.3 | Ensuring the conduct of specialised training courses, intermediate vocational education programmes, training programmes and awareness-raising campaigns | Develop vocational education programmes in the tourism sector or assist the conduct of those programmes Provide training programmes for development of the workforce Ensure the conduct of specialised training courses for the employees of persons providing tourism services for persons with disabilities Carry out awareness-raising campaigns devoted to career opportunities in the tourism sector and the activation of volunteer activities Ensure capacity-building of local self-government bodies Ensuring training and tourism development programmes in the area of HoReCa in order to fill the gap of skills (including at tourist destinations) | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Staffs of marzpets of the Republic of Armenia Local self-government bodies (upon consent) |  | 50000 | 70000 | 100000 | 120000 | 150000 | 490000 | State Budget of the Republic of Armenia, credit funds
5.1.4 | Ensuring co-operation with international educational institutions for knowledge exchange, development of systems of certification and qualification | Exchange of experience within the scope of educational programmes in the tourism sector at higher education institutions, including international higher education institutions Introducing a system of certification ensuring international qualification |  | Ministry of Education, Science, Culture and Sport of the Republic of Armenia
5.2 | Strengthen security, flexibility and preparedness for risk management through comprehensive crisis management, infrastructures adapted to climate change and systems for protection of tourists.
5.2.1 | Adoption of the Order of the Minister of Economy of the Republic of Armenia "On approving crisis and risk management programmes in the tourism sector" | Develop risk assessment and management mechanisms in the tourism sector, including a risk assessment programme in tourism, by sorting the risks and setting functions; Develop a risk management action and crisis reaction plan, which may include descriptions of the following actions: - What to do when a tourist is lost; - Emergency communication routes between tourists, guides, interested bodies; - Instructions for tourists during emergency situations (multilingual version); - Evacuation plans in hotels; - Notices for tourists in case of natural disasters; - Preparedness of tour guides in case of danger; Introduce mechanisms for co-operation with state body responsible in the sphere of emergency situations management; Develop a plan for continuation of activities and processes which may include the following information: - Maintenance of contact with customers in case of pandemic or closed borders; - Ensuring of return of customers in case of cancellation of flights; - Continuation of work remotely or with limited resources; | Tourism Committee of the Ministry of Economy of the Republic of Armenia | Ministry of Environment of the Republic of Armenia Ministry of Internal Affairs of the Republic of Armenia Ministry of Labour and Social Affairs of the Republic of Armenia Ministry of Health of the Republic of Armenia | 2026-2030 Until the second ten-day period of December of each year | [6 empty] | No financing is envisaged
5.2.2 | Introducing systems for consumer rights protection in the tourism sector | Develop security standards and guidelines in the tourism sector Develop systems for protection of and support to tourists Develop guides for communication in critical situations |  |  | 2026-2030 Until the second ten-day period of December of each year
5.2.3 | Developing a guide for improvement of tourism infrastructures adapted to climate change | Conduct climate vulnerability assessment in tourist sites, based on approaches to gathering and analysis of relevant information, climate risks analysis and other methodological approaches, as well as through field studies, interviews, climate risk management and other mechanisms; Develop climate change adaptability guidelines for persons providing tourism services Ensure availability of visitor centres in high-risk zones, with informational, medical and first aid services |  |  | 2027-2030 Until the second ten-day period of December of each year | 0 | 50000 | 50000 | 50000 | 50000 | 200000 | State Budget of the Republic of Armenia
5.3 | Promote inclusiveness and diversity in the tourism sector at the level of both employment and offered services, ensuring access and the involvement of women, youth, the elderly and persons with disabilities.
5.3.1 | Ensuring public awareness campaigns for the involvement of women, youth, the elderly and persons with disabilities in the tourism sector | Develop and implement programmes aimed at ensuring inclusiveness Develop promotion mechanisms for inclusive and accessible tourism services Develop monitoring system for diversification of the workforce | Ministry of Labour and Social Affairs of the Republic of Armenia | Tourism Committee of the Ministry of Economy of the Republic of Armenia | 2029-2030 Until the second ten-day period of December of each year | 20000 | 30000 | 40000 | 40000 | 40000 | 170000 | State Budget of the Republic of Armenia, credit funds
5.3.2 | Ensuring educational and training programmes for provision of inclusive and accessible tourism services | Develop materials of training programmes for persons providing tourism services Develop guides for accessibility and inclusiveness of tour offers Introduce mechanisms for certification of persons providing inclusive services |  |  | 2026-2028 Until the second ten-day period of December of each year
[10 empty] | Total: | 65000000

## Table 1
Table 1
Action Plan of Implementation of the 2026-2030 Strategic Plan for Tourism Development of the Republic of Armenia
TARGET MONITORING INDICATORS
N/N | STRATEGIC GOALS, PRIVATE GOALS, ACTIONS | INDICATOR | LINK TO OTHER STRATEGIC PLANNING DOCUMENT | LINK TO OTHER INTERNATIONAL COMMITMENTS OF THE CEPA, THE UN SDG | UNIT OF MEASUREMENT | BASELINE DATA (AS OF 2024) | TARGET INDICATORS
|  |  |  | other international |  |  | 2026 | 2027 | 2028 | 2029 | 2030
1 | SYSTEMATIC ACTIONS
1.1 | Improving of statistics on tourist visits | Complete statistics on inbound, outbound, domestic tourist visits and one-day visits, according to information regarding border checkpoints, number of stays, gender, age, purpose, expenditure, average duration of visit, citizenship, repeated visits and visitors' satisfaction |  |  | Data | 30% | 35% | 45% | 60% | 80% | 100%
1.2 | Conducting regular cost-benefit analyses and monitoring marketing effectiveness | Researchs, gathered data, works aimed at developing state policy in the tourism sector |  |  | Number of analyses | 0 | 1 | 1 | 1 | 1 | 1
1.3 | Regulation of the current problems in the tourism sector, issues beyond the functions and powers of the body developing the state policy | Inter-agency commission established upon the Decision of the Prime Minister of the Republic of Armenia and at least two sessions per year |  |  | Number of sessions | 0 | 2 | 2 | 2 | 2 | 2
1.4 | Adopting the draft Decision of the Prime Minister of the Republic of Armenia "On approving the Action Plan for Improving the Competitiveness of Tourism in Armenia" | Improving the position of Armenia in the Travel and Tourism Development Index |  |  | Position | 72 | ≥ 2 | ≥ 2 | ≥ 12 | ≥ 12 | ≥ 22
2 | Economic direction: Strategic Goal 1: Full use of economic potential in tourism
2.1 | Promote, through decentralisation of tourism and distribution of resources, proportional territorial development for increasing the living standard of residents, overcoming poverty and creating employment opportunities. Empower the management system, set up tourist destinations (cluster) and tourist villages, ensure the smooth functioning of tourist destination management organisations (DMO).
2.1.1 | Declaring settlements, administrative districts or administrative and territorial units, as well as their combinations, including Areni, Dilijan, Dvin, Gyumri, Jermuk, Goris, Yeghegis, containing significant tourism resource as tourist destination (cluster) | Number of improved tourist destinations (clusters) |  |  | At least piece | 0 | 2 | 3 | 2 | 0 | 0
2.1.2 | Declaring tourism villages, guided by the criteria for promoting the local culture, nature and intangible heritage | Number of improved tourist villages |  |  | At least piece | 0 | 1 | 1 | 1 | 1 | 1
3.1.2 | Improving tourism infrastructures | Improved tourist destinations and tourism villages |  |  | At least piece | 0 | 3 | 4 | 3 | 1 | 1
2.2 | Ensure the strengthening of co-operation between tourism and other sectors (agriculture, healthcare, technologies, etc.) for the purpose of ensuring the development of other sectors and promote local products and services through tourism.
2.1.2 | Ensuring cross-sectoral integration | Activating co-operation — introducing a system for promoting the use of local products in marzes |  |  | Marz | 0 | 0 | 2 | 4 | 6 | 10
2.2.2 | Developing itineraries under the title "Crossroads of Tourism" along the borderline with neighbouring countries, based on the principles of sustainable, responsible tourism, connecting cultural, natural monuments, persons providing services and manufacturers of each other, symbolising the establishment and strengthening of peace through nature and common heritage | Revitalising co-operation — carrying out joint measures |  |  | At least piece | 0 | 2 | 4 | 5 | 8 | 10
2.3 | Promote the formation of a supportive business and entrepreneurial environment in the tourism sector, by ensuring the best possible conditions for starting a business, carrying out activities and development.
2.1.3 | Introduce target systems of promotion and support for persons launching activities in the tourism sector and entities of small and medium-sized enterprises | Number of entities of small and medium-sized enterprises carrying out activities in the tourism sector which have received consulting services and support |  |  | At least piece | 0 | 10 | 25 | 50 | 80 | 100
2.4 | Engage investments, including foreign investments, to create or develop businesses through the engagement of necessary financial resources in the tourism sector.
2.4.1 | Ensuring co-operation with internationally recognised trademarks | Operation of entities of hotel industry in Armenia which are international brands |  |  | Piece | 9 | 1 | 0 | 0 | 1 | 2
2.4.2 | Ensuring the awareness of investors and their access to information | Availability/maintenance of a digital platform presenting public-private partnership programmes |  |  | Piece | 0 | 0 | 0 | 1 | 1 | 1
2.5 | Ensure the sustainability of tourism entities offering organised tour packages and their growth in the target markets.
2001-05-02 | Developing a relevant policy and ensuring access to markets for organised tourism development | Development of organised tourism (growth of the number of package tours) |  |  | % in total destinations | 5 | 5 | 5 | 5 | 6 | 6
2.5.2 | Improving tourism product and promoting business relations
2.5.3 | Capacity-building, including in the digital transformation sector
3 | International attraction direction: Strategic Goal 2. Improving the image of Armenia as an attractive tourism destination in the global market.
3.1 | Position Armenia as a boutique tourist destination, by enhancing the "Armenia: The Hidden Track" tourism brand, which places emphasis on the unique combination of cultural heritage, nature and uniqueness, and promote it through comprehensive international marketing campaigns targeted at target markets and markets with potential.
3.1.1 | Adopting and implementing the Order of the Minister of Economy of the Republic of Armenia "On approving the national tourism marketing programme under the brand "Armenia: The Hidden Track"" | Inbound tourist visits |  |  | Visit | 2200000 | 2300000 | 2400000 | 2600000 | 2800000 | 3000000
3.1.2 | Developing high-class content presenting Armenian heritage, by laying the foundation for designing a new brand
3.1.3 | Support to the conduct of cultural events, guided by representation of Armenia as a boutique destination
3.1.4 | Indirect presentation of Armenia on foreign media platforms, in immersive experiences and on entertaining programmes
3.2 | Strengthen and activate the visibility and attractiveness of Armenia in the existing and developing international markets by applying Market Penetration and Market Development strategies. Diversify markets by reducing dependence from Russian market.
3.2.1 | Strategic development and diversification of target markets, reducing dependency from Russian market | Expenditure of inbound tourist visits |  |  | USD | 1760000000 | 2001000000 | 2280000000 | 2730000000 | 3220000000 | 3780000000
3.2.2 | Managing digital marketing effectively and engaging the audience
3.2.3 | Carrying out creative campaigns in target markets
3.2.4 | Presenting Armenia in the global media field
3.2.5 | Creating and disseminating marketing materials
3.2.6 | Developing direct connections, ensuring accessibility
3.2.7 | Co-operation with markets with great potential
3.3 | Promote domestic tourism by using the opportunities shaped after the coronavirus pandemic.
3.3.1 | Ensuring the conduct of domestic tourism exhibitions and events | Domestic tourist visits |  |  | Visit | 2836749 | 3120423.9 | 3432466.29 | 3775712.919 | 4153284.2109 | 4568612.632
3.3.2 | Increasing attractiveness of leisure services through measures for service and targeted promotion of leisure in the social package
3.4 | Engage the Armenian Diaspora as ambassadors and protectors of tourism.
3.4.1 | Carrying out promotional measures targeted at Diaspora of Armenians | Growth of visits of tourists of Armenian origin |  |  | % in total visits | 35.4 | 35.5 | 36 | 37 | 38 | 39
3.5 | Promote international co-operation, regional tourism collaborations.
3.5.1 | Strengthening foreign relations in the tourism sector and ensuring co-operation with international and regional organisations | Joint actions within the scope of bilateral co-operation |  |  | Piece | 10 | 1 | 2 | 2 | 2 | 2
4. | Quality assurance direction: Strategic Goal 3․ improve tourism services
4.1 | Diversify and develop unique, experimental tourism product for the whole year (preparing tour packages based on the existing product), presenting the existing potential of cultural, gastronomical and adventure tourism destinations of Armenia, fostering the reduction of seasonality and the promotion of regular visits during the year.
4.1.1 | Designing new thematic tour itineraries, connecting tourist destinations or tourism villages — declared by the Government of the Republic of Armenia — to each other | Average extended duration of stay |  |  | Day | 5 | 5 | 5 | 6 | 6 | 6
4.1.2 | Developing a tourism product for the non-active season, based on the existing infrastructures | Average daily expenditure of a tourist |  |  | USD | 51 | 51 | 55 | 60 | 65 | 70
4.1.3 | Adopting and implementing the joint Order of the Minister of Economy of the Republic of Armenia and the Minister of Health of the Republic of Armenia "On approving the Programme for Development of Medical Tourism" Adopting and implementing the Order of the Minister of Economy of the Republic of Armenia "On approving the MICE Tourism Development Programme" | Number of individual tourists securing high revenues |  |  | Visit | 670000 | 740000 | 840000 | 900000 | 950000 | 1000000
4.2 | Improve the quality of tourism services, infrastructures and digital opportunities.
4.2.1 | Introducing an electronic register of persons providing tourism services, regulating and improving the activities of persons providing tourism services | Availability of information regarding persons providing tourism services carrying out activities in accordance with the legislation of the Republic of Armenia |  |  | Person providing services | 0 | 1000 | 200 | 300 | 400 | 500
4.2.2 | Creating audio-guides (in at least 3 languages) presenting Armenia and the Armenian tourism product at historical-cultural, natural sites and other tourist attractions in the Republic of Armenia | Availability of accurate information about Armenia and the Armenian tourism product |  |  | Historical-cultural, natural and other tourist attraction sites | 0 | 0.01 | 10 | 12 | 13 | 15
4.2.3 | Modernisation of urban and rural infrastructures | Created or improved public tourism facilities |  |  | At least piece | 15 | 5 | 6 | 1 | 2 | 2
4.2.4 | Infrastructures designed for individual passengers
4.3 | Promote the principles of responsible tourism and sustainable tourism, focusing on the informed use of nature protection and cultural values, not causing harm to the latter by ensuring social development and benefits for communities and visitors.
4.3.1 | Providing support to persons carrying out activities in the tourism sector in order to meet the criteria of sustainability certificates and quality | Qualified ersons providing services who meet international standards |  |  | Person providing services | 1 | 250 | 300 | 350 | 400 | 450
4.3.2 | Providing assistance to accessible tourism initiatives, promoting inclusiveness
4.4 | Establish regular trading opportunities at cultural and historical monuments of Armenia or their adjacent areas, enhancing profitable and sustainable economic activities in the cultural heritage sites of Armenia in order to increase the number of visitors, ensure funding for preservation and deepen public awareness about the value of those sites.
4.4.1 | Ensuring the development of profitable concession programmes | Activities of qualified destination management organisations |  |  | At least piece | 0 | 3 | 7 | 10 | 15 | 20
4.4.2 | Improving local governance capacities and expanding co-operation
4.5 | Position Armenia as a country that offers high-quality tourism services by helping Armenia become recognised as a country that offers high-quality tourism services and promote the institutional development of the tourism sector by ensuring co-ordinated and long-term growth.
4.1.5 | Introducing a qualification system that meets international standards in the tourism sector | Qualified persons providing services who meet international standards |  |  | Person providing services | 1 | 250 | 300 | 350 | 400 | 450
4.5.2 | Ensuring effectiveness of management and oversight through co-operation with interested bodies, such as ministries, inspection bodies, staffs of marzpets and local self-government bodies
5 | Social direction: Strategic Goal 4: Shape a sustainable tourism sector
5.1 | Develop human capital through international co-operation for target vocational education and the introduction of qualification systems that meet international standards. Foster the development of professional skills by ensuring preparedness of workers in the sector, engagement of international practice and introduction of high standards of qualification.
5.1.1 | Empowering the workforce of the Tourism Committee — the body developing and implementing the state policy in the tourism sector | Availability of high-class specialists in the public sector |  |  | Person | 23 | 30 | 30 | 30 | 35 | 35
5.1.2 | Ensure the operation of qualified destination management organisations (DMO) at marz or local level | Activities of qualified destination management organisations |  |  | At least piece | 0 | 3 | 7 | 10 | 15 | 20
5.1.3 | Ensuring the conduct of specialised training courses, intermediate vocational education programmes, training programmes and awareness-raising campaigns | Number of workers in the tourism sector who have undergone training |  |  | Person | 70 | 100 | 120 | 150 | 180 | 200
5.1.4 | Ensuring co-operation with international educational institutions for knowledge exchange, development of systems of certification and qualification | Persons carrying out professional activities in Armenia based on the educational base of the best international higher education institutions |  |  | Person | 3 | 3 | 3 | 3 | 5 | 5
5.2 | Strengthen security, flexibility and preparedness for risk management through comprehensive crisis management, infrastructures adapted to climate change and systems for protection of tourists.
5.2.1 | Adoption of the Order of the Minister of Economy of the Republic of Armenia "On approving crisis and risk management programmes in the tourism sector" | Guide for improvement of services |  |  | Piece | 0 | 1 | 0 | 0 | 0 | 0
5.2.2 | Ensuring consumers' awareness in the tourism sector | Guide for improvement of services |  |  | Piece | 0 | 0 | 1 | 0 | 0 | 0
5.2.3 | Developing a guide for improvement of tourism infrastructures adapted to climate change | Guide for improvement of services |  |  | Piece | 0 | 0 | 0 | 1 | 0 | 0
5.3 | Promote inclusiveness and diversity in the tourism sector at the level of both employment and offered services, ensuring access and the involvement of women, youth, the elderly and persons with disabilities.
5.3.1 | Ensuring public awareness campaigns for the involvement of women, youth, the elderly and persons with disabilities in the tourism sector | Persons ensuring involvement — in the provision of inclusive services and training courses — of persons carrying out activities in the tourism sector |  |  | Person | 0 | 50 | 50 | 50 | 50 | 50
5.3.2 | Ensuring educational and training programmes for provision of inclusive and accessible tourism services